RESTAURANT POS & OPERATIONS PLATFORM
Complete Project Development Plan

Based on the uploaded 27-page product/architecture reference document
Detailed, bit-by-bit implementation blueprint for product, engineering, database, integrations, testing and rollout

Important scope note This plan is grounded in the uploaded reference document. The source primarily provides UI/screens and menu/order examples, not a complete technical specification. Where this plan proposes APIs, database tables, architecture, security, workflows, SLAs, or implementation details that are not explicitly stated in the source, they are marked as recommended design/inference and must be confirmed during requirements workshops.

# Implementation Quick-Reference Index

Ctrl+Click any linked item below (Word desktop) to jump straight to that section. This curates the sections most load-bearing for implementation, in no particular sequence beyond the grouping; the full table of contents with every section and page number follows.

Governance & decisions

Final Approval Gate — 18-item gate that must clear before engineering starts.

Key unresolved decisions — 9 Phase 0 decisions that determine architecture scope.

Requirements Sign-off Matrix — Tracks who has (and hasn't) signed off.

Delivery sequencing

Final Bit-by-Bit Execution Sequence — The literal step-by-step build order.

Master Development Roadmap — Converts the execution sequence into phases.

Sprint-by-Sprint Development Plan — Converts the roadmap into sprints.

Core build

Order state machine — Canonical order lifecycle every module must respect.

Kitchen rules — KOT and Kitchen Display System requirements.

Online ordering & payments

Online orders live monitoring screen — Live dashboard for aggregator order monitoring.

Swiggy/Zomato & Future Aggregator Integration — Platform-agnostic model for Swiggy, Zomato, Instamart, ONDC and future channels.

Payment Gateway & Payment Management — Payment states, methods and customer-facing display.

Scale & property model

Multi-Outlet / Organization Requirements — Multi-outlet/hotel property model and PMS integration.

Initial performance targets to validate — Draft SLAs to load-test before go-live.

Cross-cutting

Risk Register — Open risks to review at every governance checkpoint.

RBAC — Role-based access model.

Non-Functional Requirements Closure — Consolidated NFRs across security, performance, availability.

Full table of contents (every section and subsection, with page numbers):

Implementation Quick-Reference Index	2

1. Document Control & Purpose	6

1.1 What the source document actually shows	6

1.2 Reference screens and evidence	7

1.3 Critical gap assessment	7

2. Executive Project Blueprint	8

2.1 End-to-end business flow	8

2.2 Recommended logical architecture	8

2.3 Recommended technology baseline	9

3. Project Governance & Delivery Model	10

3.1 Team structure	10

3.2 Environments	10

3.3 Definition of Ready	10

3.4 Definition of Done	10

4. Phase 0 – Discovery, Requirement Closure & Product Definition	11

4.1 Workshop sequence	11

4.2 Requirement register to create	11

4.3 Key unresolved decisions	11

5. Phase 1 – UX/UI, Design System & Interaction Model	12

5.1 Design principles	12

5.2 UI modules derived from the reference	12

5.3 UI state matrix	12

6. Phase 2 – Domain Architecture & Backend Foundation	13

6.1 Core domains	13

6.2 Order state machine	13

6.3 Idempotency requirements	14

6.4 API standards	14

7. Phase 3 – PostgreSQL Database Design	14

7.1 Core schema groups	14

7.2 Key database relationships	15

7.3 Database engineering rules	15

8. Phase 4 – Menu & Catalog Management	15

8.1 Category catalogue represented in the source	15

8.2 Menu item management	15

8.3 Channel synchronization	16

9. Phase 5 – Order Management & POS	16

9.1 Order types	16

9.2 Order creation sequence	16

9.3 All Orders	17

9.4 Live Orders / Running Orders	17

10. Phase 6 – Kitchen / KOT Management	17

10.1 Recommended kitchen flow	17

10.2 Kitchen rules	17

11. Phase 7 – Online Aggregator & Integration Hub	18

11.1 Integration adapter architecture	18

11.2 Inbound order workflow	18

11.3 Failure handling	18

11.4 Online orders live monitoring screen	19

12. Phase 8 – Inventory, Recipe/BOM, Purchase & Stores	20

12.1 Inventory master	20

12.2 Recommended stock movement model	20

12.3 Recipe/BOM approach	20

13. Phase 9 – Billing, Payments, Tax & Finance	21

13.1 Billing components	21

13.2 Payment state machine	21

13.3 Finance reconciliation	21

14. Phase 10 – CRM, Marketing Automation & Promotions	21

14.1 CRM baseline	21

14.2 Promotion engine	22

15. Phase 11 – Dashboard, Reporting & Analytics	22

15.1 Dashboard KPI layer	22

15.2 Reporting layers	22

16. Phase 12 – Security, Audit & Compliance	23

16.1 RBAC	23

16.2 Mandatory controls	23

17. Phase 13 – DevOps, Infrastructure & Observability	23

17.1 CI/CD pipeline	23

17.2 Observability	24

18. Phase 14 – Comprehensive Testing Strategy	24

18.1 Test levels	24

18.2 Critical end-to-end scenarios	24

19. Phase 15 – Performance & Scalability Engineering	25

19.1 Initial performance targets to validate	25

20. Phase 16 – Deployment, Migration & Rollout	25

20.1 Rollout strategy	25

20.2 Data migration	25

20.3 Rollback plan	26

21. Master Development Roadmap	26

22. Sprint-by-Sprint Development Plan	26

23. Detailed Product Backlog Structure	27

24. Production Operations & Runbooks	28

24.1 Daily health check	28

24.2 Incident priorities	28

25. Business Acceptance Checklist	28

26. Risk Register	28

27. Complete Project Deliverables Register	29

28. Source-to-Implementation Traceability	30

29. Final Bit-by-Bit Execution Sequence	30

30. Appendix – Menu Catalogue Observed in the Source	31

31. Source Notes & Limitations	32

32. Requirement Closure & Decision Framework	33

32.1 Requirement classification	33

32.2 Master decision register	33

33. Multi-Outlet / Organization Requirements	34

34. Offline POS – Complete Proposed Requirement	34

35. Inventory & Recipe/BOM – Complete Proposed Requirement	35

35.1 Proposed stock lifecycle	35

35.2 Decisions required	35

36. Tax & Pricing – Complete Proposed Requirement	35

36.1 Proposed price calculation sequence	36

37. Payment Gateway & Payment Management	36

38. Accounting Integration – Complete Proposed Requirement	36

38.1 Proposed accounting flow	37

39. Swiggy/Zomato & Future Aggregator Integration	37

39.1 Required integration data	37

39.2 Online order processing	38

40. KOT, Printer & Hardware Requirements	38

41. CRM & Customer Data	39

42. Marketing Automation	39

43. Reporting & KPI Governance	39

44. Security & Privacy Requirements	40

45. Backup, Disaster Recovery & Business Continuity	40

46. Non-Functional Requirements Closure	41

47. Recommended Release Structure	41

48. Final Approval Gate	41

49. Requirements Sign-off Matrix	42

50. Final Project Development Principle	42

# 1. Document Control & Purpose

| Item | Value |
| --- | --- |
| Document | Restaurant POS & Operations Platform – Project Development Plan |
| Source | Uploaded document: document arch.docx (27 pages) |
| Primary purpose | Convert the supplied UI/reference material into an executable software-development program. |
| Recommended delivery | Phased web/POS platform with integration-ready backend and PostgreSQL data model. |
| Audience | Product owner, restaurant operations, engineering, QA, DevOps, DBA, finance, support and integration teams. |
| Status | Planning baseline – requirements and technical assumptions require business validation. |

## 1.1 What the source document actually shows

A dashboard/home screen with sales statistics, total sales, sales by payment/category, order summaries, online orders and item performance.

Live Orders with Running Orders and Running Tables views, including dine-in, pickup and delivery concepts.

All Orders with date/time filtering, order type, order status, amounts, payment information, customer/order details, export and invoice-related actions.

Online Orders Activity with channels including Swiggy and Zomato, plus delivery-order status and action controls.

KOT (Kitchen Order Ticket) listing with order type, customer name/phone, item count/name, status, bill print date, completion duration and created time.

Menu/online-menu management with channel tabs, recent/all views, Swiggy/Zomato references, stock update, name/online display name, category filters and status filters.

A large menu catalogue containing categories such as Breakfast, Meal Box (Online), Rice Bowls (Online), beverages, soups, starters, curries, roti, noodles, biryani, flavour rice, desserts, fresh juice, Meals N.I, buttermilk/lassi, mocktails, milk shakes and extra items.

Menu item states of Off, Partial Changes, On and Unscheduled, plus examples of individual item availability.

## 1.2 Reference screens and evidence

Pages 1–5 visually establish the main operational dashboard, live orders, all orders, online-order activity, KOT and a module/quick-navigation view. Page 6 introduces online menu management. Pages 7–27 enumerate menu categories, items and availability states. filecite-style references are provided in the accompanying response; this document uses page references for traceability.

## 1.3 Critical gap assessment

The reference does not fully specify user roles, exact business rules, tax configuration, recipe/BOM logic, inventory valuation, purchasing workflow, payment gateway behavior, delivery partner APIs, accounting rules, loyalty rules, CRM fields, multi-outlet behavior, offline synchronization, deployment topology, security controls, or reporting definitions. These must be closed during Phase 0 before production implementation.

# 2. Executive Project Blueprint

The recommended product should be treated as a modular restaurant operations platform rather than a single POS screen. The UI evidence indicates a connected flow from menu configuration → order capture → kitchen/KOT → fulfilment → payment/invoice → inventory/finance/reporting → integrations.

## 2.1 End-to-end business flow

1. Master setup: outlet, users, roles, taxes, payment methods, menu categories, items, pricing and availability.

2. Channel setup: dine-in, pickup, delivery and external online channels.

3. Customer/order capture: order created from POS or integrated channel.

4. Order validation: price, availability, taxes, discounts, service/delivery charges and payment rules.

5. Kitchen orchestration: KOT created; items routed to relevant preparation station(s).

6. Preparation: KOT status progresses through configured kitchen states.

7. Fulfilment: dine-in served, pickup handed over, delivery dispatched/completed.

8. Billing/payment: invoice/bill generated; payment recorded and reconciled.

9. Inventory impact: ingredients/stock consumption and adjustments recorded according to confirmed recipe/BOM rules.

10. Analytics: transaction events feed dashboard, reports, finance and operational KPIs.

11. Audit/support: all critical changes recorded with actor, timestamp, outlet and before/after values.

## 2.2 Recommended logical architecture

Recommended design (not explicitly specified by the source):

Web Admin/POS UI
        │
        ▼
API Gateway / BFF
        │
 ┌──────┼─────────┬─────────┬─────────┐
 ▼      ▼         ▼         ▼         ▼
Auth   Orders    Menu      Inventory Finance/Reports
 │      │         │         │         │
 └──────┴─────────┴─────────┴─────────┘
        │
        ▼
PostgreSQL + Redis + Object Storage + Message/Event Layer
        │
        ├── Swiggy/Zomato/other channel adapters
        ├── Payment adapters
        ├── Printer/KOT/receipt adapters
        └── Reporting/analytics pipeline

For an initial release, a modular monolith is recommended unless scale, team boundaries or integration volume justify independent microservices. This reduces operational complexity while preserving module boundaries.

## 2.3 Recommended technology baseline

| Layer | Recommended baseline | Reason |
| --- | --- | --- |
| Frontend | React/Next.js or equivalent TypeScript SPA/PWA | Fast dashboard development, reusable components, responsive POS/admin UI. |
| Backend | TypeScript Node.js/NestJS or Java/Spring Boot | Strong modular APIs, validation, RBAC and integration support. |
| Database | PostgreSQL | Transactional integrity for orders, billing, inventory and finance. |
| Cache | Redis | Sessions, short-lived state, rate limits, menu caching and real-time coordination. |
| Async/events | RabbitMQ/Kafka/SQS-equivalent | Reliable external integrations and asynchronous processing. |
| Object storage | S3-compatible storage | Invoices, exports, attachments and generated documents. |
| Observability | OpenTelemetry + centralized logs + metrics | Production troubleshooting and auditability. |
| Deployment | Containers + Kubernetes or managed container platform | Repeatable deployment and horizontal scaling. |
| CI/CD | Git + CI pipeline + automated tests + deployment gates | Controlled release process. |

# 3. Project Governance & Delivery Model

## 3.1 Team structure

| Role | Primary responsibility | Key outputs |
| --- | --- | --- |
| Product Owner | Business decisions and prioritization | Backlog, acceptance decisions, release priorities |
| Business Analyst | Requirement discovery and process mapping | BRD, workflows, acceptance criteria |
| Solution Architect | System and integration architecture | HLD, LLD review, architecture decisions |
| UX/UI Designer | Convert reference screens into production UX | Design system, wireframes, prototypes |
| Frontend Engineers | POS/admin web application | UI modules, state management, API integration |
| Backend Engineers | Domain services and APIs | APIs, business rules, integrations |
| DBA/Data Engineer | Schema, performance and reporting data | Migrations, indexes, backups, reporting model |
| QA Engineers | Functional, integration and regression testing | Test cases, automation, release sign-off |
| DevOps/SRE | Environments, CI/CD and observability | Infrastructure, deployment, monitoring |
| Security | Security architecture and testing | Threat model, controls, VAPT remediation |
| Support/Operations | Production operations | Runbooks, incident handling, training |

## 3.2 Environments

DEV – developer integration and unit/integration testing.

QA – controlled functional testing and automation.

UAT – business validation using representative restaurant workflows.

STAGING – production-like deployment and release rehearsal.

PRODUCTION – live operations with controlled change management.

## 3.3 Definition of Ready

Business owner identified.

Workflow documented.

Field-level requirements available.

Validation rules agreed.

Dependencies/integrations identified.

Acceptance criteria written.

UI states and error states defined.

Security/permission impact identified.

## 3.4 Definition of Done

Code reviewed and merged.

Unit and integration tests pass.

Database migration tested.

API contract documented.

UI responsive and accessible to agreed standard.

Audit logging implemented for critical changes.

Security checks completed.

Performance baseline completed.

QA passed and UAT acceptance recorded.

Release notes and rollback steps prepared.

# 4. Phase 0 – Discovery, Requirement Closure & Product Definition

Objective: remove ambiguity before significant engineering investment. Duration recommendation: 2–3 weeks.

## 4.1 Workshop sequence

| Workshop | Participants | Outputs |
| --- | --- | --- |
| Business process discovery | PO, BA, outlet operations | Current/future-state process maps |
| Order lifecycle | PO, kitchen, billing, delivery | Order state machine |
| Menu & pricing | PO, menu admin | Menu master rules and availability model |
| Inventory | Stores, purchase, kitchen, finance | Stock movement and valuation rules |
| Finance | Finance, billing | Tax, payment, invoice, settlement rules |
| Integration | Integration, operations | Channel/payment/printing contracts |
| Security/RBAC | PO, security, admin | Role-permission matrix |
| Reporting | Management, finance, operations | KPI dictionary and report definitions |

## 4.2 Requirement register to create

Outlet/branch master requirements.

User/employee and role requirements.

Menu category/item/variant/modifier requirements.

Channel-specific menu mapping requirements.

Price list and effective-date requirements.

Order types and order lifecycle.

KOT and kitchen station behavior.

Customer master and CRM requirements.

Inventory, recipe/BOM and wastage requirements.

Purchase/GRN/vendor/stock adjustment requirements.

Payment, tax, invoice and settlement requirements.

Marketing/loyalty/promotion requirements.

Reports and dashboard KPI definitions.

External aggregator integration requirements.

Audit, security and compliance requirements.

## 4.3 Key unresolved decisions

| Decision | Why it matters | Decision owner |
| --- | --- | --- |
| Single outlet vs multi-outlet | Changes all major keys, permissions and reporting. | Product Owner |
| Recipe/BOM based inventory or manual deduction | Determines inventory architecture. | Operations/Finance |
| Offline POS required? | Changes sync/conflict architecture. | Product Owner/IT |
| Payment gateway vs POS-only payments | Changes integration and reconciliation. | Finance |
| Which aggregator/e-commerce platforms (e.g., Swiggy, Zomato, Swiggy Instamart, ONDC network, others)? | Determines adapter/API scope, commission/payout model and delivery-fulfilment mode (platform-owned rider vs self-delivery). | Business |
| Tax jurisdiction/rules | Affects invoice calculations. | Finance/Tax |
| Printer/KOT hardware model | Determines device integration. | Operations/IT |
| Accounting system integration | Determines finance export/API design. | Finance/IT |
| Customer loyalty/CRM depth | Determines CRM scope. | Marketing |

# 5. Phase 1 – UX/UI, Design System & Interaction Model

Objective: turn the supplied visual reference into a complete production-ready design system. Duration recommendation: 3–4 weeks, overlapping with backend discovery.

## 5.1 Design principles

Dashboard-first: high-value operational metrics visible immediately.

Fast POS interaction: minimize clicks and modal depth.

Operational status must be visually obvious but not color-dependent alone.

Every table must support search, filter, sort, pagination and export where applicable.

Critical actions require confirmation and permission checks.

All modules should preserve outlet/date context.

Design desktop admin and touch-friendly POS interactions separately where needed.

## 5.2 UI modules derived from the reference

| Module | Reference evidence | Build scope |
| --- | --- | --- |
| Dashboard | Sales statistics, sales chart, order summaries, leakage and item performance | KPI cards, charts, filters, drill-downs, alert widgets |
| Live Orders | Running Orders, Running Tables, pending orders | Real-time order board, status transitions, SLA timers |
| All Orders | Trend chart, filters, order table, export/invoice actions | Search/filter/export/detail/refund/cancel where approved |
| Online Orders | Swiggy/Zomato tabs and delivery status | Channel inbox, retry, acknowledgement, sync status |
| KOT | KOT list and completion duration | Kitchen queue, station routing, status transitions |
| Menu Management | Categories/items/status/channel controls | Item master, availability, online display name, bulk actions |
| Quick navigation | Products/Operations/Reports/Settings style launcher | Role-aware module launcher |

## 5.3 UI state matrix

| State | Meaning to confirm | Required UI behavior |
| --- | --- | --- |
| On | Available/active | Show as active; allow ordering |
| Off | Unavailable/inactive | Prevent new orders; preserve existing orders |
| Partial Changes | Some channel/item attributes changed | Show differences and synchronization state |
| Unscheduled | No scheduled availability rule | Show default availability behavior |

The source explicitly shows these four menu states, but does not define their exact business semantics. Final semantics must be approved in Phase 0. fileciteturn2file2L105-L110

# 6. Phase 2 – Domain Architecture & Backend Foundation

Objective: build the stable domain foundation before implementing every UI screen.

## 6.1 Core domains

Identity & Access

Organization/Outlet

Menu & Catalog

Pricing & Tax

Order Management

Kitchen/KOT

Customer/CRM

Inventory

Purchase & Vendor

Payments & Billing

Marketing/Promotions

Reporting & Analytics

Integration Hub

Notifications

Audit & Configuration

## 6.2 Order state machine

Recommended state model; exact states must be aligned with the business:

DRAFT – order being created.

PLACED – order successfully accepted.

CONFIRMED – order validated and accepted by outlet.

KOT_CREATED – kitchen ticket generated.

IN_PREPARATION – kitchen processing.

READY – preparation complete.

ASSIGNED – delivery/pickup handoff prepared where applicable.

OUT_FOR_DELIVERY – delivery dispatched.

SERVED/HANDED_OVER – customer fulfilment completed.

COMPLETED – financial/operational completion.

CANCELLED – order cancelled with reason.

FAILED – technical/business failure requiring retry or support.

## 6.3 Idempotency requirements

Every external order must have a channel order identifier.

Every inbound webhook/event must have an idempotency key.

Order creation must not create duplicate orders on network retry.

Payment callbacks must be idempotent.

Menu synchronization must be versioned.

Inventory deductions must reference the originating transaction/event.

## 6.4 API standards

REST/JSON or agreed RPC contract with versioned endpoints.

Consistent error object: code, message, field errors, correlation ID.

Pagination using cursor or page/limit consistently.

Filtering and sorting through validated allow-lists.

Authentication through short-lived access tokens and secure refresh mechanism.

RBAC/ABAC checks at service layer, not UI only.

OpenAPI specification maintained as a release artifact.

# 7. Phase 3 – PostgreSQL Database Design

Objective: establish a transactional schema that supports high-volume order capture, kitchen operations, menu synchronization, payments and future inventory/finance extensions.

## 7.1 Core schema groups

| Domain | Recommended tables |
| --- | --- |
| Identity | users, roles, permissions, user_roles, role_permissions, sessions |
| Organization | organizations, outlets, stations, terminals, business_hours |
| Catalog | categories, menu_items, item_variants, modifiers, modifier_groups, menu_channels |
| Availability | item_availability, availability_schedules, channel_item_mapping |
| Pricing | price_lists, item_prices, taxes, tax_rules, discounts |
| Customers | customers, customer_addresses, customer_tags, customer_notes |
| Orders | orders, order_items, order_item_modifiers, order_status_history, order_payments |
| Kitchen | kitchen_orders, kot_tickets, kot_items, kitchen_stations, station_routes |
| Inventory | ingredients, stock_locations, stock_balances, stock_movements, recipes, recipe_items, wastage |
| Purchase | vendors, purchase_orders, purchase_order_items, goods_receipts, goods_receipt_items |
| Finance | invoices, invoice_items, payments, refunds, settlements, ledger_entries |
| Marketing | campaigns, coupons, promotions, loyalty_accounts, loyalty_transactions |
| Integration | integrations, channel_accounts, inbound_events, outbound_events, sync_jobs |
| Audit | audit_logs, configuration_changes, access_logs |
| Reporting | daily_sales_summary, hourly_sales_summary, item_sales_summary, payment_summary |

## 7.2 Key database relationships

Outlet → Terminal → User sessions
Category → Menu Item → Variant/Modifier
Menu Item ↔ Channel Mapping
Customer → Order → Order Item → KOT Item
Order → Invoice → Payment/Refund
Menu Item → Recipe → Ingredient → Stock Movement
Purchase Order → Goods Receipt → Stock Movement
Integration Account → Inbound Event → Order/Sync Job

## 7.3 Database engineering rules

Use UUID or another globally unique identifier strategy for distributed integrations.

Keep immutable transaction records; use status history instead of destructive updates for critical workflows.

Add created_at, updated_at, created_by, updated_by where appropriate.

Use unique constraints for outlet-scoped business identifiers.

Index foreign keys and high-selectivity filters.

Use partial/compound indexes for operational queues such as active orders and pending KOTs.

Use database migrations only; never manual schema edits in production.

Define retention/archive strategy for high-volume order/event/audit data.

Use transactions for order + payment + inventory operations where atomicity is required.

# 8. Phase 4 – Menu & Catalog Management

The reference devotes most of its pages to menu/category and availability configuration. This makes catalog management a core module, not a minor master-data screen.

## 8.1 Category catalogue represented in the source

The source lists categories including Breakfast, Meal Box (Online), Rice Bowls (Online), Cold Beverage, Hot Beverages, Soup(Veg), Meals, Soup(Non-Veg), Chinese Starters (Veg/Non-Veg), Tandoori Starters (Veg/Non-Veg), Curries (Veg/Non-Veg), Roti, Noodles (Veg/Non-Veg), Biryani (Veg/Non-Veg), Flavour Rice (Veg/Non-Veg), Dessert, Fresh Juice, Meals N.I, Butter Milk & Lassi, MOCKTAILS, Milk Shakes and Extra items. fileciteturn1file1L41-L99

## 8.2 Menu item management

Create/edit item.

Assign category and subcategory where required.

Set internal name and online display name.

Configure channel visibility.

Configure price(s) and effective dates.

Configure tax category.

Configure item availability state.

Configure scheduled availability.

Configure stock/availability dependency.

Configure modifiers/add-ons.

Configure preparation/KOT station.

Support bulk enable/disable operations.

Maintain audit history.

## 8.3 Channel synchronization

The reference explicitly exposes Online/Recent/All and Swiggy/Zomato views, along with a stock update action and online display name. fileciteturn2file0L16-L28

Admin changes item availability.

System validates permission and outlet/channel mapping.

Change is stored with a version number.

Integration job generates channel-specific payload.

Payload is queued.

Adapter sends to external channel.

Response is persisted.

UI shows synchronized/failed/pending state.

Retry is safe and idempotent.

Audit record stores who changed what and when.

# 9. Phase 5 – Order Management & POS

The reference screens show operational views for live/running orders, running tables, all orders and online order activity. fileciteturn2file0L11-L15

## 9.1 Order types

Dine-in

Pickup

Delivery

External online/aggregator order

Room service / in-room dining, linked to guest name, room number and stay folio

Banquet/event order, supporting bulk quantities, pre-order menus and guaranteed headcount

Additional order types only if confirmed during discovery

## 9.2 Order creation sequence

Select outlet/terminal/session.

Select order type.

Select table/customer/delivery information as applicable.

Add menu items.

Apply modifiers and notes.

Validate item availability.

Calculate item subtotal.

Calculate discounts/promotions.

Calculate taxes and charges.

Calculate grand total.

Select payment or mark payment pending based on order type.

Create order transaction.

Generate KOT if required.

Publish real-time update to kitchen/order board.

Return order number and printable/displayable receipt.

## 9.3 All Orders

Date/time range filter.

Order type filter.

Order status filter.

Order/customer search.

Payment status filter.

Order detail drawer/page.

Invoice generation/print where permitted.

Export with permission.

Refund/cancellation actions with reason and audit.

Operational timeline showing created → kitchen → fulfilment → completion.

## 9.4 Live Orders / Running Orders

Real-time refresh or push updates.

Separate running and pending sections.

Dine-in/pickup/delivery segmentation.

Elapsed preparation/fulfilment time.

Priority/SLA indication.

Operator actions based on permission.

No duplicate status transitions.

# 10. Phase 6 – Kitchen / KOT Management

The source shows a KOT listing with order type, customer name/phone, item count, item names, status, bill print date, completion duration, created time and actions. fileciteturn2file0L15-L15

## 10.1 Recommended kitchen flow

Order accepted.

KOT generated.

KOT routed to station.

Station acknowledges ticket.

Items move to preparation.

Items become ready.

KOT is completed.

Order moves to fulfilment/serve/handover.

## 10.2 Kitchen rules

A KOT must be traceable to one order and its items.

Item-level status is required if split preparation is possible.

KOT changes must be auditable.

Cancellation after preparation begins requires a reason and permission.

Preparation duration should be computed from timestamps, not manually typed.

Kitchen display should recover state after browser/device restart.

Kitchen display shows one panel per station with live queue count and average ticket age.

Tickets are colour-coded by elapsed time against a configurable SLA threshold (for example green/amber/red).

An expo/pass screen consolidates all stations' items for a single order into one bump view before release.

New and ageing tickets trigger an audible and visual alert distinguishable from routine updates.

Items can be rerouted to an alternate station of the same type when one station's queue exceeds its configured capacity.

# 11. Phase 7 – Online Aggregator & Integration Hub

The source shows Swiggy and Zomato as online channels and exposes online order activity. fileciteturn2file0L17-L28

## 11.1 Integration adapter architecture

Integration Hub
  ├─ Channel Account Manager
  ├─ Inbound Webhook Receiver
  ├─ Outbound API Client
  ├─ Mapping Engine
  ├─ Retry/Dead-letter Queue
  ├─ Sync Status Store
  └─ Reconciliation Service

## 11.2 Inbound order workflow

Receive webhook/polling event.

Authenticate/verify source.

Persist raw event before business processing.

Check idempotency.

Map external item/channel identifiers to internal IDs.

Validate availability and pricing policy.

Create/update internal order.

Generate KOT.

Acknowledge external channel.

Publish status to UI.

Record processing outcome and correlation ID.

## 11.3 Failure handling

Temporary network error → exponential retry.

Duplicate event → return idempotent success/no duplicate order.

Unknown item mapping → quarantine event and alert operator.

Invalid price/tax mapping → quarantine or business-defined fallback.

External API rejection → persist error and expose manual retry.

Repeated failure → dead-letter queue and operational alert.

Kitchen queue depth per station is monitored against a configurable capacity threshold; breaching it can auto-pause or auto-86 affected items on the originating channel.

Peak-hour and multi-outlet concurrent order-ingestion targets must be defined and load-tested before go-live, in addition to the steady-state performance targets in Phase 15.

## 11.4 Online orders live monitoring screen

This screen consolidates every inbound online/aggregator order across platforms into one real-time operational view, separate from the sales-focused KPI dashboard in Phase 11.

Summary bar showing live order count, count per platform, orders breaching SLA, and orders currently paused or failed.

Platform filter (Swiggy, Zomato, Swiggy Instamart, ONDC, others) and outlet filter for multi-outlet organizations.

Live list of orders sorted oldest-first by default, with manual sort by platform, status or value.

Auto-refresh via real-time push; no manual reload required to see a new order.

Consolidated across outlets for a duty-manager/NOC view, and scoped to a single outlet for outlet-level staff, per permission.

| Field | Description |
| --- | --- |
| Platform & platform order ID | Source channel and the external order reference. |
| Order age / timer | Elapsed time since order received, counting up. |
| SLA indicator | Colour-coded against the configured acceptance/preparation threshold (green/amber/red). |
| Customer name & masked phone | Customer identity as supplied by the platform. |
| Item summary | Item count and expandable full item list with modifiers. |
| Order value | Item subtotal, discounts, taxes and grand total. |
| Payment status | Prepaid (platform-settled) or cash-on-delivery, with payment state. |
| Order status | New, accepted, preparing, ready, rider assigned, picked up, delivered, cancelled. |
| KOT status link | Linked KOT and its kitchen-station status. |
| Delivery/rider details | Rider name, phone and ETA where delivery is platform-owned. |
| Cancellation/refund flag | Present if a cancellation or refund event was received from the platform. |
| Actions | Accept/reject, print KOT, mark ready, escalate — shown per permission and order status. |

A new order triggers a distinct audible and visual alert until it is acknowledged.

An SLA breach (order not accepted or not ready within its configured threshold) escalates visually and, if configured, notifies the duty manager.

A quarantined or failed integration event (per Phase 7 failure handling) appears here as an actionable item, not only in a technical log.

Selecting an order opens the same order-detail view used in All Orders, keeping timeline and audit history consistent across screens.

# 12. Phase 8 – Inventory, Recipe/BOM, Purchase & Stores

Inventory is not fully described in the supplied pages; the architecture should therefore be designed as an extensible domain and confirmed in discovery.

## 12.1 Inventory master

Ingredient/material master.

Unit of measure and conversion.

Stock location/store.

Opening stock.

Minimum/reorder level.

Supplier/vendor mapping.

Batch/lot and expiry if required.

Costing method.

Wastage reason.

## 12.2 Recommended stock movement model

| Movement | Source transaction | Effect |
| --- | --- | --- |
| RECEIPT | Goods receipt | Increase stock |
| ISSUE | Store issue | Decrease stock |
| CONSUMPTION | Recipe/order | Decrease stock |
| WASTAGE | Wastage record | Decrease stock |
| TRANSFER_OUT | Inter-store transfer | Decrease source |
| TRANSFER_IN | Inter-store transfer | Increase destination |
| ADJUSTMENT+ | Approved adjustment | Increase stock |
| ADJUSTMENT- | Approved adjustment | Decrease stock |
| RETURN | Purchase/supplier return | Decrease stock |

## 12.3 Recipe/BOM approach

Define recipe for each sellable menu item where inventory automation is required.

Each recipe references ingredients and quantities.

Order completion/consumption event creates stock-consumption movements.

Wastage and manual adjustments remain separate transaction types.

Reversals are compensating transactions rather than destructive edits.

# 13. Phase 9 – Billing, Payments, Tax & Finance

## 13.1 Billing components

Bill/invoice numbering.

Customer billing details.

Itemized charges.

Discounts.

Taxes.

Service/delivery/other charges if applicable.

Payment method.

Payment status.

Refund/void handling.

Settlement and reconciliation.

## 13.2 Payment state machine

INITIATED → PENDING → SUCCESS

INITIATED → FAILED

SUCCESS → REFUNDED/PARTIALLY_REFUNDED

All transitions must be immutable/auditable.

## 13.3 Finance reconciliation

Collect POS transactions.

Collect online channel transactions.

Collect payment gateway transactions where applicable.

Match by order/payment/reference IDs.

Identify unmatched or partial settlements.

Generate reconciliation report.

Post approved accounting entries or export to accounting system.

# 14. Phase 10 – CRM, Marketing Automation & Promotions

The reference navigation includes CRM and Marketing Automation labels, although detailed business rules are not provided in the visible source pages. Therefore this module should be implemented after the core transaction engine and after requirements confirmation.

## 14.1 CRM baseline

Customer profile.

Contact details.

Addresses.

Order history.

Preferences/tags.

Consent/preferences where applicable.

Feedback/complaints.

Loyalty identifier if approved.

## 14.2 Promotion engine

Promotion definition.

Eligibility rules.

Item/category/outlet scope.

Date/time window.

Usage limits.

Coupon code.

Stacking/exclusion rules.

Approval and audit.

Promotion impact reporting.

# 15. Phase 11 – Dashboard, Reporting & Analytics

The first reference screen is strongly dashboard-oriented, showing sales statistics, sales visualization, order-type summaries, online orders and item performance. fileciteturn2file0L11-L12

## 15.1 Dashboard KPI layer

| KPI | Calculation principle | Drill-down |
| --- | --- | --- |
| Gross Sales | Sum of qualifying sales before selected deductions | Orders/items/outlet |
| Net Sales | Gross sales minus configured deductions | Order/payment |
| Order Count | Count of completed/qualifying orders | Order list |
| Average Order Value | Net sales / order count | Order list |
| Dine-in Sales | Sales from dine-in orders | Orders |
| Pickup Sales | Sales from pickup orders | Orders |
| Delivery Sales | Sales from delivery orders | Orders |
| Online Sales | Sales from configured online channels | Channel/order |
| Top Items | Rank by quantity or revenue | Item sales |
| Payment Mix | Sales grouped by payment method | Payment transactions |
| KOT Duration | Completion timestamp minus creation/start | KOT detail |

## 15.2 Reporting layers

Operational reports – current orders, pending KOT, online failures.

Sales reports – daily/hourly/category/item/channel.

Payment reports – method-wise, settlement and reconciliation.

Inventory reports – stock, consumption, wastage, movement.

Purchase reports – vendor, PO, receipt and price history.

Finance reports – invoice, tax, refund and ledger export.

Customer reports – repeat customers, frequency, average spend.

Management dashboards – outlet comparison and trends.

Live operations dashboard – real-time KOT backlog per station and outlet, delayed-ticket alerts against SLA, and aggregator channel health, for kitchen and duty-manager monitoring.

# 16. Phase 12 – Security, Audit & Compliance

## 16.1 RBAC

| Role family | Typical permissions |
| --- | --- |
| Super Admin | Platform configuration and cross-outlet administration |
| Outlet Manager | Outlet operations, reports, controlled configuration |
| POS Operator/Cashier | Create orders, collect payments, print bills |
| Kitchen User | View/update KOT within assigned stations |
| Menu Admin | Catalog, pricing/availability within permission |
| Inventory User | Stock, receipts, issues, adjustments |
| Purchase User | Vendors, PO, GRN |
| Finance User | Invoices, payments, refunds, settlements |
| Marketing/CRM User | Customer and promotion workflows |
| Auditor/Read Only | Read-only reports/audit |

## 16.2 Mandatory controls

Least privilege.

MFA for administrative accounts where supported.

Password/session controls.

Encryption in transit and at rest.

Secrets stored in a secret manager.

Audit logging for configuration, price, menu status, refunds, cancellations and permission changes.

Rate limiting on public/integration endpoints.

Input validation and output encoding.

Dependency and container vulnerability scanning.

Regular backup restore testing.

Production access through controlled identities.

# 17. Phase 13 – DevOps, Infrastructure & Observability

## 17.1 CI/CD pipeline

Developer creates branch.

Lint + static analysis.

Unit tests.

Build frontend/backend.

Dependency/security scan.

Container build.

Integration tests.

Database migration validation.

Deploy to DEV.

QA approval.

Deploy to UAT/STAGING.

Business approval.

Production change approval.

Production deployment.

Smoke test.

Release monitoring.

## 17.2 Observability

Application logs with correlation ID.

API latency and error metrics.

Order creation success/failure rate.

KOT processing latency.

External integration success/failure/retry counts.

Database CPU/connections/locks/slow queries.

Queue depth and dead-letter counts.

Infrastructure health.

Business alerts such as sudden order failure or channel disconnect.

# 18. Phase 14 – Comprehensive Testing Strategy

## 18.1 Test levels

| Level | Coverage |
| --- | --- |
| Unit | Pricing, tax, state transitions, validation, permission logic |
| Component/UI | Forms, tables, filters, dashboard widgets, POS controls |
| API | CRUD, authorization, validation, idempotency, pagination |
| Integration | Payment, aggregator, printer/KOT, inventory |
| End-to-end | Complete order-to-payment workflows |
| Regression | Existing functionality after every release |
| Performance | Concurrent order creation, dashboard queries, integration spikes |
| Security | Auth, RBAC, injection, session, secrets, API abuse |
| Recovery | DB restore, queue retry, failed deployment, external outage |
| UAT | Real restaurant workflows and acceptance criteria |

## 18.2 Critical end-to-end scenarios

Dine-in order → KOT → serve → payment → completion.

Pickup order → KOT → ready → customer handover.

Delivery order → KOT → dispatch → delivered → payment/settlement.

Online aggregator order → inbound event → mapping → KOT → fulfilment → status callback.

Item switched OFF → new orders blocked → existing order remains valid.

Item switched ON → item becomes orderable after successful channel sync.

Partial channel change → only intended channel configuration changes.

Duplicate webhook → one internal order only.

Payment callback repeated → one payment transaction only.

Cancellation after KOT → permission/reason/audit validation.

Refund → payment/order/report reconciliation.

Stock shortage → defined behavior: block/substitute/alert, according to approved business rule.

# 19. Phase 15 – Performance & Scalability Engineering

## 19.1 Initial performance targets to validate

| Area | Recommended starting target | Validation |
| --- | --- | --- |
| POS order save | p95 < 500 ms excluding external dependency | Load test |
| Dashboard initial data | p95 < 2 seconds for standard date range | Performance test |
| KOT update | Near-real-time, target < 1 second internal propagation | Event test |
| Search/list APIs | p95 < 500 ms under expected load | Load test |
| External integration | Async; user UI should not block on slow partner APIs | Failure test |
| Database | No unbounded full-table scans on critical paths | Query plan review |

Important These are engineering targets proposed for planning, not source requirements. Replace them with formally approved SLAs/SLOs after traffic and outlet volumes are known.

# 20. Phase 16 – Deployment, Migration & Rollout

## 20.1 Rollout strategy

Pilot with one outlet or controlled test environment.

Load representative menu and configuration.

Validate POS/order/KOT/payment workflows.

Validate online integrations if applicable.

Run parallel validation against existing process.

Train outlet users.

Go live during controlled window.

Hypercare for first operating period.

Measure defects and operational KPIs.

Roll out to additional outlets in waves.

## 20.2 Data migration

Extract existing menu master.

Normalize categories and item names.

Map external channel IDs.

Load prices and taxes.

Load customers if approved.

Load opening inventory if in scope.

Validate record counts and totals.

Run reconciliation report.

Obtain business sign-off before cutover.

## 20.3 Rollback plan

Freeze deployment.

Preserve transaction/event data.

Disable affected integration if required.

Restore application version.

Do not delete transactions; reconcile compensating transactions.

Verify database health and operational flows.

Communicate rollback and recovery status.

# 21. Master Development Roadmap

| Phase | Duration | Primary outputs | Exit gate |
| --- | --- | --- | --- |
| 0. Discovery | 2–3 weeks | BRD, workflows, backlog, decisions | Requirements sign-off |
| 1. UX/UI | 3–4 weeks | Design system, prototypes | UX approval |
| 2. Architecture/Foundation | 2–3 weeks | HLD, API standards, repo, CI/CD | Architecture review |
| 3. Database | 2–3 weeks | Schema, migrations, seed strategy | DB review |
| 4. Menu | 3–4 weeks | Catalog and availability | Menu UAT |
| 5. POS/Orders | 4–6 weeks | Order lifecycle and billing | Order UAT |
| 6. KOT | 2–3 weeks | Kitchen workflow | Kitchen UAT |
| 7. Integrations | 4–6 weeks | Aggregator/payment adapters | Integration certification |
| 8. Inventory/Purchase | 4–6 weeks | Stock and purchase | Inventory UAT |
| 9. Finance | 3–4 weeks | Invoices/payment/reconciliation | Finance sign-off |
| 10. CRM/Marketing | 3–5 weeks | Customer/promotion workflows | Marketing UAT |
| 11. Reporting | 3–4 weeks | Dashboard/reports | KPI sign-off |
| 12–15. Security/DevOps/Test/Performance | 4–6 weeks | Hardening and release readiness | Go-live approval |
| 16. Pilot/Rollout | 2–4 weeks | Production pilot and rollout | Production acceptance |

With parallel workstreams, a practical first production release could be approximately 16–24 weeks, subject to scope, team size, integration certification and whether inventory/finance/CRM are included in the first release. This is a planning estimate, not a source-stated deadline.

# 22. Sprint-by-Sprint Development Plan

| Sprint | Focus | Major deliverables |
| --- | --- | --- |
| Sprint 0 | Discovery | Stakeholder workshops, process maps, requirement register, architecture decisions |
| Sprint 1 | Foundation | Repository, CI/CD, auth skeleton, base layout, database migration framework |
| Sprint 2 | Master data | Outlet, users, roles, categories, initial menu item CRUD |
| Sprint 3 | Menu | Pricing, status, availability schedules, channel mapping |
| Sprint 4 | POS | Order creation, cart, modifiers, pricing/tax engine |
| Sprint 5 | Order lifecycle | Order states, order list, detail, cancellations |
| Sprint 6 | KOT | KOT generation, kitchen queue, status updates |
| Sprint 7 | Billing | Invoice, payment recording, receipt |
| Sprint 8 | Online integration | Inbound event receiver, mapping, idempotency |
| Sprint 9 | Outbound sync | Menu sync/status, retries, reconciliation |
| Sprint 10 | Inventory | Ingredient/stock master, movements, adjustments |
| Sprint 11 | Purchase | Vendor, PO, GRN, stock receipt |
| Sprint 12 | Finance | Refunds, settlement, reconciliation |
| Sprint 13 | CRM/Marketing | Customer history, promotions, basic campaigns |
| Sprint 14 | Reports | Dashboard KPIs, exports, operational reports |
| Sprint 15 | Hardening | Security, performance, regression, observability |
| Sprint 16 | UAT | Business scenarios, defect closure, training |
| Sprint 17 | Pilot | Production pilot, hypercare, monitoring |
| Sprint 18+ | Rollout | Wave deployment and optimization |

# 23. Detailed Product Backlog Structure

| ID | Epic | Story/Capability | Priority |
| --- | --- | --- | --- |
| AUTH-001 | Authentication | User login/logout/session | Critical |
| AUTH-002 | RBAC | Role and permission matrix | Critical |
| OUT-001 | Outlet | Create/manage outlet and operating hours | Critical |
| MENU-001 | Category | Create/edit category | Critical |
| MENU-002 | Item | Create/edit menu item | Critical |
| MENU-003 | Availability | On/Off/Partial/Unscheduled | Critical |
| MENU-004 | Channel | Channel mapping and display name | High |
| MENU-005 | Schedule | Scheduled item availability | High |
| ORD-001 | POS | Create dine-in/pickup/delivery order | Critical |
| ORD-002 | Order status | State transitions and history | Critical |
| ORD-003 | Order search | Filter/search all orders | High |
| KOT-001 | KOT | Generate KOT from order | Critical |
| KOT-002 | Kitchen | Kitchen queue and status | Critical |
| PAY-001 | Payment | Record payment | Critical |
| PAY-002 | Refund | Controlled refund flow | High |
| INT-001 | Inbound | Receive external order | High |
| INT-002 | Idempotency | Duplicate-event protection | Critical |
| INV-001 | Stock | Stock movement engine | High |
| PUR-001 | Purchase | PO and GRN | Medium |
| CRM-001 | Customer | Customer profile/history | Medium |
| MKT-001 | Promotion | Promotion/coupon engine | Medium |
| RPT-001 | Dashboard | Sales/order KPIs | Critical |
| RPT-002 | Exports | CSV/XLSX/PDF exports as approved | Medium |
| AUD-001 | Audit | Critical action audit log | Critical |

# 24. Production Operations & Runbooks

## 24.1 Daily health check

Application health endpoints.

Database health and replication/backup status if applicable.

Queue depth and dead-letter events.

External channel connectivity.

Payment/integration error rates.

Failed orders and KOT backlog.

Disk and memory utilization.

Backup completion.

Audit/security alerts.

## 24.2 Incident priorities

| Priority | Example | Response objective |
| --- | --- | --- |
| P1 | POS unavailable across outlet(s) | Immediate incident bridge and service restoration |
| P2 | Online orders failing or payment integration degraded | Rapid mitigation and partner escalation |
| P3 | Single report/menu issue | Normal operational support |
| P4 | Minor UI defect | Backlog/next release |

# 25. Business Acceptance Checklist

Dashboard totals reconcile with order transactions.

Order totals reconcile with invoice totals.

Payment totals reconcile with payment records.

KOT count and item quantities match order items.

Menu status behavior matches approved business definitions.

External channel item mappings are correct.

External order IDs are never duplicated.

Cancellation/refund permissions are enforced.

Reports reproduce agreed KPI definitions.

Inventory movements reconcile to approved stock events if inventory is in scope.

Audit logs identify user, outlet, action, timestamp and affected record.

Backup and restore test has passed.

Production monitoring and alerting are operational.

Business users have completed training.

# 26. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Unclear business rules | High | Phase 0 decision register and signed acceptance criteria |
| Aggregator API changes | High | Adapter abstraction, contract tests and monitoring |
| Duplicate online orders | High | Idempotency keys and persisted inbound events |
| Incorrect pricing/tax | High | Centralized pricing engine and reconciliation |
| Slow dashboard queries | Medium | Pre-aggregations, indexes and query monitoring |
| Inventory mismatch | High | Immutable stock movements and reconciliation |
| POS network outage | High | Offline strategy decision in Phase 0 |
| User permission leakage | High | Server-side RBAC + security tests |
| Poor adoption | Medium | Pilot, training and workflow usability testing |
| Deployment failure | High | CI/CD gates, rollback plan and backups |

# 27. Complete Project Deliverables Register

Business Requirements Document (BRD)

Functional Requirements Specification (FRS)

Process/workflow catalogue

Role & Permission Matrix

UX wireframes and high-fidelity UI designs

Design system/component library

Solution Architecture / HLD

Detailed Design / LLD

API specification/OpenAPI

PostgreSQL ERD and data dictionary

Database migration scripts

Integration contracts and adapter specifications

Test strategy and test cases

Automated regression suite

Performance test report

Security/threat model and VAPT remediation report

CI/CD pipeline configuration

Infrastructure-as-code

Monitoring dashboards and alert rules

Deployment runbook

Backup/restore runbook

Incident response runbook

User manuals and training material

UAT sign-off

Production readiness checklist

Go-live and rollback plan

Post-go-live hypercare report

# 28. Source-to-Implementation Traceability

| Source evidence | Implementation area | Traceability |
| --- | --- | --- |
| Dashboard with sales statistics, order summaries and item performance (p.1) | Dashboard/reporting | Dashboard KPI and analytics epic |
| Running Orders/Running Tables and pending orders (pp.1–2) | Order management | Live order board + state machine |
| All Orders with filters, trend and actions (pp.2–3) | Order management/reporting | Order search/filter/export/detail |
| Online Orders Activity and Swiggy/Zomato (p.4) | Integration Hub | Aggregator adapter and order ingestion |
| KOT list and completion duration (p.5) | Kitchen | KOT workflow and SLA metrics |
| Online/Recent/All + Swiggy/Zomato + stock update (p.6) | Menu/channel management | Channel mapping, availability and sync |
| Category and status filters (pp.7–10) | Catalog | Category and availability master |
| Menu item catalogue across pp.10–27 | Catalog seed/master | Item/category import and master-data validation |

# 29. Final Bit-by-Bit Execution Sequence

Freeze the scope of Release 1.

Run discovery workshops and produce the decision register.

Confirm single/multi-outlet model.

Confirm exact order types and order states.

Confirm tax, pricing, discount and payment rules.

Confirm menu availability semantics: On/Off/Partial/Unscheduled.

Confirm external channels and API credentials/contract availability.

Confirm inventory/recipe scope for Release 1.

Confirm finance/accounting integration scope.

Approve UX information architecture.

Approve design system and reference-screen mapping.

Create repositories, branching policy and CI/CD.

Create PostgreSQL baseline schema and migrations.

Implement authentication/RBAC.

Implement outlet/configuration masters.

Implement category/item/variant/modifier catalog.

Implement pricing/tax calculation engine.

Implement menu availability and scheduling.

Implement POS cart and order creation.

Implement order lifecycle and status history.

Implement KOT generation and kitchen queue.

Implement invoice and payment recording.

Implement dashboard and order reports.

Implement external channel adapter framework.

Implement inbound online order ingestion.

Implement menu/channel synchronization.

Implement retry/idempotency/reconciliation.

Implement inventory stock movement engine if approved.

Implement purchase/GRN if approved.

Implement finance reconciliation if approved.

Implement CRM/marketing if approved.

Complete automated tests.

Complete performance/security testing.

Complete UAT.

Train users.

Run production pilot.

Monitor hypercare.

Fix pilot defects.

Roll out in waves.

Perform post-implementation review and backlog next release.

# 30. Appendix – Menu Catalogue Observed in the Source

The following is a representative source-derived catalogue structure, not a normalized production master. It should be imported only after business validation.

| Category | Representative source items |
| --- | --- |
| Breakfast | Idly Sambar, Vada Sambar, Ghee Karam Idly, 70 Mm Dosa, Paper Dosa, Set Dosa, Onion Uttapam, Rava Dosa, Poori, Upma, Breakfast Buffet, Kids Buffet, Breakfast Combo, Thatte Idly |
| Meal Box (Online) | Telangana Executive Box Veg, North Indian Meal Box, South Indian Meal Box, Dal Khichdi Box, Executive Meal Box (egg), Telangana Executive Box Non Veg, Dal Khichdi Box (Non-Veg), Curd Rice Box |
| Rice Bowls (Online) | Aloo 65 Sambar Rice Bowl, Jeera Rice Bowl With Paneer Butter Masalaa, Butter Chicken Jeera Rice Bowl, Chicken 65 Sambar Rice Bowl, Chicken Biryani + Sambar Rice + Curd Rice, Steam Rice W/ Telangana Chicken Curry |
| Cold Beverage | Alakaline, Maaza 250ml |
| Hot Beverages | Boost, Horlicks, Strong Filter Coffee |
| Soups | Corn Soup, Veg Hot & Sour Soup, Veg Manchow Soup, Chicken Manchow Soup, Chicken Hot & Sour Soup |
| Chinese Starters | Veg Manchurian, Crispy Corn, Paneer Majestic, Paneer Manchurian, Rampuri Paneer, Baby Corn Manchuria, Paneer Tikka, Chilly Paneer, Andhra Paneer Vepudu; Chicken Majestic, Chicken Manchuria, Chilly Chicken, Pepper Chicken, Rampuri Chicken, Loose Prawns, Apollo Fish, Egg Chilli, Masala Omelette, Boild Egg, Rampuri Prawns |
| Tandoori Starters | Kapila Veg Starters, Kapila Special Veg Kabab, Chicken Tikka, Tandoori Chicken Half/Full, Tangdi Kabab Half/Full, Kapila Special Chicken Kebab, Kapila Non Veg Starter |
| Curries | Dal Fry, Dal Tadka, Kadai Veg, Mixed Veg Curry, Mushroom Butter Masala, Kadai Paneer, Paneer Butter Masala, Kaju Butter Masala, Palak Paneer, Kapila Spl Veg Curry, Methi Chaman; Butter Chicken, Kadai Chicken, Telangana Chicken Curry, Egg Curry, Egg Burji, Kapila Spl Chicken Curry, Extra Chicken Curry, Egg Keema Masala, Telangana Mutton Curry, Desi Chicken |
| Roti | Plain Naan, Butter Naan, Garlic Butter Naan, Tandoori Roti, Aloo Paratha, Paneer Paratha, Butter Roti, Phulka 2pcs |
| Noodles | Veg Soft Noodles, Schezwan Veg Noodles, Manchurian Noodles, Egg Soft Noodles, Chicken Soft Noodles, Schezwan Chicken Noodles |
| Biryani | Veg Biryani, Chicken Dum Biryani, Chicken Fry Piece Biryani, Special Chicken Biryani (boneless), Fish Biryani, Prawns Biryani, Egg Biryani, Mini Chicken Dum Biryani, Mini Chicken Dum Biryani (Double Masala), Kapila Spl Non Veg Pulao, Mutton Kheema Pulao |
| Flavour Rice | Veg Pulao, Kaju Paneer Pulao, Dal Khichdi, Jeera Rice, Tomato Rice, Veg Fried Rice, Sambar Rice, Veg Kheema Pulao, Egg Fried Rice, Double Egg Fried Rice, Chicken Fried Rice |
| Dessert | Apricot Delight, Kulfi With Rabri, Jamun Ka Ghosla, Brownie With Icecream, Brownie With Chocolate Sauce, Cheese Kunafa, Kunafa Choco Dream, Kunafa Choco Vanilla, Mini Apricot Delight |
| Beverage/Other | Black Grape Juice, Executive Meals Non-veg, Chocolate Lassi, Mint Mojito, Blue Lagoon, Watermelon Burst, Fresh Lemon Soda, Ginger Sparkler, Kalakatta Syrup, Virjin Mint Mojito, Choco Brownie Milk Shake, Biscoff Milkshake, Kitkat Milkshake, Oreo Milkshake, Cold Coffee Milkshake, Rose Gulkand Milkshake, Cold Coffee |
| Extra items | Chapathi, Extra Poori (meals), Extra Chicken Curry (meals) |

# 31. Source Notes & Limitations

The uploaded reference is 27 pages and is heavily visual; several pages are screenshots rather than detailed textual requirements.

The document provides strong evidence for UI structure and menu catalogue/availability concepts.

The document does not, by itself, establish the complete technical architecture, exact business rules, database schema, API contracts, security model or operational SLAs.

All recommended architecture and engineering decisions in this plan should be validated through formal discovery before development is considered contractually complete.

Where the source shows an item as ON/OFF, that state is reproduced as source evidence; it is not interpreted as a universal business rule beyond what the screen demonstrates.

# 32. Requirement Closure & Decision Framework

This section completes the major gaps identified in the reference. The uploaded 27-page source remains authoritative for the visible screens, terminology, menu catalogue and operational concepts. Any requirement below that is not explicitly supported by the source is marked PROPOSED or DECISION REQUIRED. It must be approved by the Product Owner before it becomes a committed business rule.

## 32.1 Requirement classification

| Class | Meaning | Engineering treatment |
| --- | --- | --- |
| SOURCE | Directly visible/stated in the uploaded document. | Treat as baseline reference behavior. |
| PROPOSED | Recommended design added to close a gap. | Validate before locking business rules. |
| DECISION REQUIRED | Source does not provide enough information. | Obtain explicit owner decision. |
| CONFIGURABLE | Behavior should vary by outlet/business policy. | Implement configuration, not hard-coded logic. |

## 32.2 Master decision register

| ID | Area | Recommended baseline | Owner |
| --- | --- | --- | --- |
| DEC-001 | Multi-outlet | Design for Organization → Outlet → Terminal; Release 1 may launch one outlet. | PO/IT |
| DEC-002 | Offline POS | Controlled offline queue for order capture if uninterrupted POS operation is required. | PO/IT |
| DEC-003 | Inventory | Recipe/BOM consumption plus stock movements, wastage and adjustments. | Operations/Finance |
| DEC-004 | Tax | Centralized configurable tax engine with effective dates. | Finance |
| DEC-005 | Payments | Cash/card/UPI plus configurable online payment adapters. | Finance/IT |
| DEC-006 | Accounting | Vendor-neutral accounting adapter/export layer. | Finance |
| DEC-007 | Aggregators | Adapter architecture for Swiggy/Zomato and future channels. | Business/IT |
| DEC-008 | KOT hardware | Printer/display abstraction with station-level routing. | Operations/IT |
| DEC-009 | CRM | Customer profile, history, tags and consent; loyalty-ready schema. | PO/Marketing |
| DEC-010 | Reporting | Transactional source of truth plus reporting summary layer. | PO/Finance |
| DEC-011 | Security | RBAC, audit, encryption, secrets management and privileged MFA. | Security/IT |
| DEC-012 | DR | Backups, restore testing and approved RPO/RTO. | IT/SRE |

# 33. Multi-Outlet / Organization Requirements

STATUS: DECISION REQUIRED. The source does not define whether the product is single-outlet or multi-outlet. PROPOSED BASELINE:

Support multiple outlets in the data model from day one, even if the first production deployment has only one outlet.

Every transaction and operational record must be attributable to an outlet.

Users can be assigned to one or more outlets.

Roles can be global or outlet-scoped.

Menu, pricing, tax, availability, inventory and integrations should be outlet-aware.

Reports can operate at outlet level and consolidated organization level subject to permissions.

A single hotel property may operate multiple F&B outlets (restaurant, bar, poolside, banquet) sharing or independently assigned to kitchen stations.

Property Management System (PMS) integration for room-charge posting and folio reconciliation is a decision required in Phase 0 if room service or in-room dining is in scope.

| Entity | Purpose |
| --- | --- |
| Organization | Top-level business/tenant. |
| Outlet | Physical restaurant location. |
| Terminal | POS register/device. |
| Kitchen Station | Preparation area/printer/display destination. |
| User Assignment | User-to-outlet authorization scope. |

# 34. Offline POS – Complete Proposed Requirement

STATUS: DECISION REQUIRED. Offline behavior is not specified in the source. If business continuity is required, use the following controlled model:

Cache the last approved menu, prices, taxes and outlet configuration.

Detect loss of backend connectivity and visibly enter Offline mode.

Allow order capture using the cached configuration.

Generate device-local transaction IDs and local sequence numbers.

Queue transactions in protected local storage.

Generate KOT using the approved local print/display mechanism.

When connectivity returns, authenticate the device and upload queued transactions.

Use idempotency keys to prevent duplicate server-side orders.

Server returns canonical IDs and synchronization status.

Conflicts or invalid records enter an exception queue for operator/admin resolution.

Payment behavior during offline mode must be separately approved. Do not assume an online gateway can authorize payments while the POS has no network connectivity.

# 35. Inventory & Recipe/BOM – Complete Proposed Requirement

STATUS: DECISION REQUIRED. The source does not contain enough inventory detail to establish final rules.

Ingredient/material master with unit of measure and conversion.

Store/location master.

Supplier/vendor master.

Recipe/BOM per sellable menu item.

Modifier/add-on ingredient consumption where applicable.

Opening stock, receipt, issue, transfer, consumption, wastage and adjustment movements.

Reorder/minimum levels.

Optional batch/expiry tracking.

Immutable stock movement ledger.

Approval workflow for significant stock adjustments/wastage.

## 35.1 Proposed stock lifecycle

Purchase Order created.

Goods Receipt recorded.

Accepted quantity increases stock.

Store issue/transfer creates stock-out movement.

Recipe consumption creates consumption movement.

Wastage creates separate wastage movement.

Stock count creates approved adjustment.

Every movement retains source transaction, actor, timestamp and location.

## 35.2 Decisions required

| Question | Proposed default | Owner |
| --- | --- | --- |
| When is ingredient consumed? | At completed/approved operational event; make configurable. | Operations |
| Negative stock? | Blocked by default; emergency override requires permission. | Operations |
| Costing? | FIFO or weighted average; finance must choose. | Finance |
| Batch/expiry? | Enable where required by ingredient/business policy. | Operations |
| Stock count? | Frequency by category/store; define during UAT. | Operations |
| Wastage approval? | Threshold-based approval. | Operations/Finance |

# 36. Tax & Pricing – Complete Proposed Requirement

STATUS: DECISION REQUIRED. Exact tax rules are absent from the source.

Centralize tax calculation in the backend.

Assign tax categories to menu items/prices.

Support effective-dated tax rules.

Preserve historical invoice calculations even after future rule changes.

Define discount-before-tax versus discount-after-tax behavior.

Define rounding policy centrally.

Audit every price/tax configuration change.

Never hard-code tax rates in frontend code.

## 36.1 Proposed price calculation sequence

Base item price.

Variant/modifier additions.

Quantity.

Eligible discount/promotion.

Taxable amount.

Tax calculation.

Approved service/delivery/other charges.

Rounding.

Grand total.

Payment allocation.

# 37. Payment Gateway & Payment Management

STATUS: DECISION REQUIRED. Payment fields are visible in the reference, but gateway contracts are not provided.

Payment methods should be configurable: cash, card, UPI/digital payment, online gateway and external-channel settlement.

Persist payment reference, method, amount, status, timestamps and external reference.

Support INITIATED, PENDING, SUCCESS, FAILED, REFUNDED and PARTIALLY_REFUNDED states where applicable.

Payment callbacks must be idempotent.

Unknown gateway states remain pending until reconciled.

Manual payment overrides require elevated permission and audit.

Refunds must reference the original payment.

A customer-facing display shows the bill total, itemized summary and a QR/UPI code for guest-scanned payment.

Split-bill is supported by item, by equal share among guests, or by mixed tender (for example part cash, part card) against a single order.

Tip/gratuity captured at the point of payment is recorded against the transaction and included in payment-method reporting.

Final gateway/vendor, terminal behavior, settlement cycle and refund policy must be approved by Finance/IT.

# 38. Accounting Integration – Complete Proposed Requirement

STATUS: DECISION REQUIRED. No accounting product or posting rules are defined in the source.

Keep POS transactions independent of a specific accounting vendor.

Create an accounting adapter interface.

Map sales, tax, discounts, payments, refunds and settlements to finance accounts.

Queue accounting postings asynchronously so accounting downtime does not block POS.

Persist external accounting reference IDs.

Provide posted/pending/failed/unmatched reconciliation states.

Support period-close controls so historical transactions are not silently altered.

## 38.1 Proposed accounting flow

Completed operational transactions are selected.

Finance summary/posting candidates are generated.

Account/tax/payment mappings are applied.

Posting payload is created.

Payload is queued and sent.

External response/reference is stored.

Failures are retried or sent to manual resolution.

Finance reconciliation confirms the period.

# 39. Swiggy/Zomato & Future Aggregator Integration

SOURCE: The reference visibly includes Swiggy and Zomato and an Online Orders Activity screen. Exact API contracts are not supplied, so the following is an implementation architecture rather than a claim about partner APIs.

The same adapter framework and data model apply uniformly to every current and future platform (for example Swiggy, Zomato, Swiggy Instamart, ONDC network participants, or a direct ordering website/app) — platforms differ only in their configured scope, commission/payout terms and delivery-fulfilment mode, not in the underlying integration code.

| Capability | Internal service |
| --- | --- |
| Receive online order | InboundOrderHandler |
| Accept/reject | OrderAcknowledgementService |
| Update order status | OrderStatusPublisher |
| Menu synchronization | MenuSyncService |
| Availability update | AvailabilityPublisher |
| Item/channel mapping | MappingService |
| Retry/dead-letter | IntegrationRetryService |
| Settlement/reconciliation | ReconciliationService |
| Commission & payout reconciliation | PayoutReconciliationService |
| Delivery/logistics status tracking | LogisticsStatusService |

## 39.1 Required integration data

Channel account.

Channel outlet/location mapping.

Channel item mapping.

Channel order mapping.

Inbound event store.

Outbound event store.

Sync job records.

Retry attempts.

Integration errors.

Reconciliation records.

Platform scope register — Swiggy, Zomato, Swiggy Instamart, ONDC network and any additional platform, per outlet, with onboarding and API-credential status.

Commission and payout rule per platform (commission percentage, payout cycle, TDS/GST deduction basis).

Delivery-fulfilment mode per platform and order (platform-owned rider network vs restaurant self-delivery).

Channel-specific price list, where the menu price on a platform differs from the POS price to absorb commission.

## 39.2 Online order processing

Receive webhook or poll response.

Authenticate/verify the source.

Persist raw event.

Check idempotency.

Map external IDs to internal items/outlet.

Validate business rules.

Create/update internal order.

Generate KOT.

Acknowledge external channel.

Publish status to UI.

Persist processing result and correlation ID.

Duplicate event → no duplicate order.

Temporary failure → retry with backoff.

Unknown item → quarantine and alert.

Partner rejection → persist error and expose manual retry.

Repeated failure → dead-letter queue.

Rider/logistics status received from the platform (assigned, picked up, delivered) is reflected on the order for platform-owned delivery.

Order acceptance and preparation-time SLA is tracked per platform, since most platforms penalise late acceptance or long preparation time.

Cancellation or refund raised on the platform is received as an event and reconciled against the internal order and payment record.

An outlet can be paused on an individual platform without affecting other channels, consistent with the kitchen-capacity throttling defined for high order volume.

# 40. KOT, Printer & Hardware Requirements

STATUS: KOT is demonstrated in the source; exact hardware is not.

Use a print-service abstraction rather than coupling application code to one printer model.

Support KOT, customer receipt and invoice templates separately.

Route KOTs to configured kitchen stations.

Persist print-job status.

Failed print jobs are visible and retryable.

Hardware replacement is configuration-driven.

Prevent accidental duplicate prints through controlled job IDs and operator feedback.

# 41. CRM & Customer Data

STATUS: CRM appears in the navigation, but detailed requirements are absent. PROPOSED BASELINE:

| Entity | Minimum scope |
| --- | --- |
| Customer | Name, phone, email, status, created/updated metadata. |
| Address | Delivery addresses and type. |
| Tags | Segmentation labels. |
| History | Customer-order relationship. |
| Feedback | Rating/comment/status linked to order/customer. |
| Consent | Communication purpose, status and timestamp. |
| Loyalty | Optional points/balance structure ready for future use. |

# 42. Marketing Automation

STATUS: The reference includes a Marketing Automation navigation item but does not define the workflows. PROPOSED Release-2 scope:

Customer segmentation.

Campaign creation.

Coupon/promotion rules.

Eligibility and usage limits.

Scheduling.

Communication-channel abstraction.

Campaign performance.

Consent/opt-out enforcement.

Audit.

# 43. Reporting & KPI Governance

SOURCE: The dashboard clearly shows sales statistics, sales visualization, order-type summaries, online orders and item performance. Exact KPI formulas are not supplied. fileciteturn2file0L11-L15

PostgreSQL transactional data remains the operational source of truth.

Reporting summaries may be pre-aggregated for performance.

Every KPI gets a documented formula.

Every report has a timezone and date-range definition.

Exports preserve filters and generated timestamp.

Large reports run asynchronously where required.

| KPI | Decision that must be documented |
| --- | --- |
| Gross Sales | Which order states and charges are included? |
| Net Sales | How are discounts, refunds and taxes treated? |
| Order Count | Which states qualify? |
| AOV | Exact numerator and denominator? |
| Online Sales | Which channels qualify? |
| Payment Mix | Order payment or settlement basis? |
| Item Performance | Revenue, quantity or both? |
| KOT Duration | Which timestamps define start/end? |

# 44. Security & Privacy Requirements

STATUS: Not defined in source. PROPOSED BASELINE:

Backend-enforced RBAC and outlet authorization.

Privileged MFA.

Secure session/token handling.

TLS for network traffic.

Encryption for sensitive data at rest.

Secrets manager for credentials.

Audit logs for menu/price/status/refund/cancellation/permission changes.

API rate limiting.

Input validation and secure output handling.

Dependency/container vulnerability scanning.

Controlled production database access.

Permission-controlled data export.

PII minimization and access logging.

# 45. Backup, Disaster Recovery & Business Continuity

STATUS: Not defined in source. PROPOSED BASELINE:

| Area | Proposed requirement |
| --- | --- |
| Database backup | Automated backups plus point-in-time recovery where supported. |
| Backup monitoring | Alert on failed or stale backups. |
| Restore testing | Regular restore drill with evidence. |
| RPO | Business-approved target; proposed starting point ≤15 minutes. |
| RTO | Business-approved target; proposed starting point ≤1 hour for critical service. |
| Integration recovery | Durable inbound/outbound events prevent data loss during partner outage. |
| Runbook | Named owners and step-by-step recovery procedure. |

The RPO/RTO values above are planning proposals, not requirements from the uploaded document.

# 46. Non-Functional Requirements Closure

| Category | Proposed baseline |
| --- | --- |
| Availability | Business-approved availability target with defined outage behavior. |
| Performance | Critical POS APIs target p95 <500 ms excluding external dependencies. |
| Scalability | Scale by outlets, concurrent users, orders/hour and integration volume. |
| Reliability | Idempotency, durable events and transactional integrity. |
| Maintainability | Modular domains, API contracts, automated tests. |
| Observability | Logs, metrics, traces and business alerts. |
| Recoverability | Backup/restore and DR procedures. |
| Localization | Timezone, currency and number/date formatting configurable. |

# 47. Recommended Release Structure

This is a project-management recommendation, not a source-derived requirement.

| Release | Recommended scope |
| --- | --- |
| R1 – Core POS | Auth/RBAC, outlet, menu, pricing/tax, POS, Live Orders, All Orders, KOT, billing, dashboard and audit. |
| R1.1 – Online | Aggregator framework, approved Swiggy/Zomato integrations, online orders, menu availability sync and reconciliation. |
| R2 – Inventory/Finance | Recipe/BOM, stock, purchase, GRN, finance reconciliation and accounting adapter. |
| R2 – CRM/Marketing | Customer profile, segmentation, promotions and basic campaigns. |
| R3 – Scale | Advanced offline, multi-outlet analytics, advanced BI and optimization. |

# 48. Final Approval Gate

Before requirements are considered frozen, the following decisions must be signed off:

Release 1 scope.

Single-outlet versus multi-outlet strategy.

Order types and order state machine.

Menu availability semantics for On/Off/Partial/Unscheduled.

Pricing, discount, tax and rounding rules.

Payment methods and gateway scope.

Offline POS requirement and payment behavior during offline mode.

Inventory consumption event and recipe/BOM policy.

Negative stock policy.

Accounting product/integration scope.

Swiggy/Zomato and future aggregator scope.

KOT printer/display hardware.

CRM and marketing scope.

Dashboard KPI formulas.

RBAC matrix.

Backup, RPO/RTO and DR targets.

UAT acceptance criteria.

Production support ownership and escalation.

# 49. Requirements Sign-off Matrix

| Area | Business owner | Technical owner | Status |
| --- | --- | --- | --- |
| Order management | Operations/PO | Solution Architect | PENDING |
| Menu/catalog | Operations/Menu | Engineering | PENDING |
| Tax/pricing | Finance | Backend Lead | PENDING |
| Payments | Finance/PO | Integration Lead | PENDING |
| Inventory | Stores/Operations | Backend/DBA | PENDING |
| Accounting | Finance | Integration Lead | PENDING |
| Aggregators | Business/IT | Integration Lead | PENDING |
| CRM/Marketing | Marketing/PO | Engineering | PENDING |
| Security | Security/IT | Security Architect | PENDING |
| Infrastructure/DR | IT/SRE | DevOps/SRE | PENDING |
| Reports/KPIs | Management/Finance | Data/Backend | PENDING |

# 50. Final Project Development Principle

The project is now structured as a requirements-to-development program rather than only a UI recreation. The source-derived features remain traceable to the uploaded document, while missing business and technical decisions are explicitly separated. The next engineering step is to convert every APPROVED decision into a formal requirement, user story, acceptance criteria, API contract, database rule and automated test.